## Sheet1
Codeshare Project schedule
Deadline
April 19th
SA | Comments on Chap. 7 from Trevor
SA | Check if Chap. 9 needs comments
CA | Discontinuation rates for Chap. 7
SA | Finish Chap. 7
CA/SA | Review Chap. 9 code
May 5th
| CA | Review Chap. 7 code
| SA | Finish Chap. 8
| CA | Finish Chap. 4
May 30th
|  | CA | Review Chap. 4 code
|  | SA | Review Chap. 8 code
June 15th
|  |  | CA | Finish Chap. 5
|  |  | SA | Finish Chap. 10
June 20th
|  |  |  | SA | Review Chap. 5 code
July 1st
[5 empty] | CA | Review Chap. 10 code
[5 empty] | SA/CT | Finish Chap. 12
[5 empty] | CA | Finish Chap. 6
July 15th
[6 empty] | SA | Review chap. 6 code
[6 empty] | CA | Review chap. 12 code